## BCA Estimate Summary
SUMMARY
EMI Branch/ CSIT/ COR Hours Estimate | 653.12
Contractor Hours Estimate | 0
Contractor Cost Estimate | 0

## BCA Level of Effort (TIME)
INSTRUCTIONS: Fill in only cells in Column B, and Development cell at E14. All other cells are locked and will auto populate based on these entries.
PROJECT NAME | Sample | Activity | Staff Hours | Staff Days | FORMULA NOTES
Type of course (IS, ILT) | Self Study - IS | Est. Design/ Development Level of Effort | 292.5 | 36.5625 | Number of pages developed by EMI staff at a rate of 1.5 pages per hour (includes cycles of revision)
New Development or existing course revision | Existing Course Total Revision (Over 50% change) | Est. Deliverable Review Level of Effort | 20.1 | 2.5125 | Number of pages reviewed by EMI staff at a rate of 10 pages per hour
Percentage of in-house (EMI) work (0.1 - 1) | 0.5 | Curriculum Standards/ 508 Level of Effort | 62.52 | 7.815 | Curriculum Standard reviews at a rate of 20% of Review, Design and Development
Percentage of Contracted work (0 - .09) | 0.5 | Est. Focus Group Level of Effort by EMI Staff | 72 | 9 | Focus group hours x 3 for prep and close out (1.5 staff x 3)
Estimated contract length (months) | 12 | Est. Stakeholder Review Level of effort by EMI Staff | 20 | 2.5 | Stakeholder reviews with average of 10 comments per reviewer and adjudication of 5 comments per hour
Length of course or courses under this development or revision (contact hours) | 3 | Est. Pilot Level of Effort by EMI Staff | 18 | 2.5714 | Pilot offering hours x 3 for prep and close out (2 staffx3)
Length of course or courses under this development or revision (days) - Each 7 contact hours= 1 day | 0.3 | COR level of effort for SOW development, contract meetings and invoices | 168 | 21 | 2 week development+ 1 hour per week x months of contract+ 1 week close out
Estimated page count for of all course materials (for ILT:BCA/UTNA, POI, IG, SM, Visuals, Activities and supplemental materials/ for IS number of online pages) | 67 | TOTAL ESTIMATED EMI LEVEL OF STAFF EFFORT: | 653.12 | 81.9614
% of course materials requiring development or revision ( (0.1 - 1) | 1 | Staff year expenditure | 37.43% |  | 219 day staff year after average leave and federal holidays
Days of planned Focus Group meetings | 2
Number of stakeholder engagement/comment periods | 2
Estimated number of Stakeholders for each review period | 5 | HOURS - ISD Design/Development level of effort to develop 1 classroom hour (Current EMI average is 65-75 ISD hours to develop 1 classroom hour) | 195 | https://sites.google.com/site/instructionaldesignandtraining/perspectives/time-to-develop-one-hour-of-training
Number of planned course Pilot offerings | 1 |  |  | How Long Does It Take to Develop Training? New Question, New Answers (td.org)
Cycles of Review (minimum 3: Initial Draft, Final Draft, Final Product) | 3 |  |  | Estimating Costs and Time in Instructional Design (nwlink.com)

## BCA Cost Estimate ($)
Length of course or courses under this development or revision (contact hours) | 2 |  | Labor Category | Cost/ Hour | Contractor Hours | Contractor $
Length of course or courses under this development or revision (days) - Each 7 contact hours= 1 day | 0.28571 |  | Manager/ QA | 170 | 0 | 0
Estimated page count for of all course materials (for ILT:BCA/UTNA, POI, IG, SM, Visuals, Activities and supplemental materials/ for IS number of online pages) | 130 |  | Editor | 80 | 0 | 0
% of course materials requiring development or revision ( (0.1 - 1) | 1 |  | Designers/ Programmers | 125 | 0 | 0
Percentage of in-house (EMI) work (0.1 - 1) | 1 |  | SMEs | 155 | 0 | 0
Percentage of Contracted work (0 - .09) | 0 |  | TOTAL |  | 0 | 0
Hours to ptroduce 1 hour or training from TIME sheet | 195
| EMI ISD | Contract ISD
ISD Hours estimate based on Hours or Training | 292.5 | 0

## FEEDER
Type of Course | Type of Development
Self Study - IS | Existing Course Minor Revision (under 25% change)
Instructor Led | Existing Course Major Revision (25-50% Change)
Existing Course Total Revision (Over 50% change)
New Course Development